## Matrix
RACI
AutoSocDeploy
| Tâche | Status | Luis |  |  |  | Khalil |  |  |  | Massyl
Phase 0
| Constitution et validation des groupes et sujet | Fait | R | A |  |  |  |  | C | I |  |  | C | I
| Créer dépôt Github et Trello | Fait | R | A |  |  |  |  | C | I |  |  | C | I
Phase 1
| Serveur AD : Mise en place de Splunk Entreprise avec Ansible | Fait | R | A |  |  |  |  | C | I |  |  | C | I
| Serveur Web : Mise en place d'un Linux avec un Honeypot Wordpress | Fait | R | A |  |  |  |  | C | I |  |  | C | I
| Serveur Windows : Mise en place d'un Windows 10 pro avec un Honeypot | En cours | C | I |  |  |  |  | R | A |  |  | R | A
Phase 2
| Serveur Windows : Sysmon configuré sur le poste W10 pro client avec Ansible | Fait |  |  | C | I | R | A |  |  | R | A
| Serveur Web : Auditd configuré sur le Serveur Web avec Ansible | Fait | R | A |  |  |  |  | C | I |  |  | C | I
| Serveur AD : Splunk server reçoit des logs des 2 machines avec Ansible | Fait |  |  | C | I | R | A |  |  | R | A
| Serveur AD : Début construction de règles, alertes sur splunk avec Ansible | En cours | R | A | C | I | R | A | C | I | R | A | C | I
Phase 3
| Serveur AD : Construction de règles, alertes sur splunk avec Ansible |  |  |  | C | I | R | A |  |  | R | A
| Début mise en place d'une solution qui test nos alertes Splunk |  |  |  | C | I | R | A |  |  | R | A
Phase 4
| Réalisation d'une analyse d'infra (nmap) |  |  |  | C | I | R | A |  |  | R | A
| Tester une attaque sur AD (smbexec ou autre...) |  |  |  | C | I | R | A |  |  | R | A
| Amélioration infra |  | R | A |  |  |  |  | C | I |  |  | C | I
Phase 5
| Dernières modifications, date de fin du projet |  | R |  | C | I |  | A | C | I |  | A | C | I
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## About
RACI MATRIX TEMPLATE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/raci-matrix.html
© 2018 Vertex42 LLC
About This Template
Use this template within your project team to help clarify and communicate roles and responsibilities for each task or deliverable. Start by inserting rows to define the tasks and deliverables and insert columns as needed to define the roles of sponsors, leaders, consultants, and project team members. Customize the abbreviations below the chart based on the method you are using (RACI, DRASCI, CAIRO, etc.).
Terms of Use / Copyright
This template is a copyrighted work. Do not submit copies or modifications of this template to any website or online template gallery. Click on the link below to learn how you may or may not use this template.
License: Private Use Only
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.